SEO Growth Plan

2× Organic MQL Leads by December 2026

Prepared: 15 June 2026  ·  Data: GSC Jan–May 2026, Ahrefs June 2026, HubSpot 157 MQL contacts

1. Baseline: Where We Are Now

GSC Traffic Trend (monthly)

| Month | Clicks | Impressions | CTR | Avg Position |
| --- | --- | --- | --- | --- |
| Dec 2025 | 5,993 | 1.66M | 0.36% | 10.0 |
| Jan 2026 | 7,021 | 2.23M | 0.31% | 9.8 |
| Feb 2026 | 7,021 | 2.45M | 0.29% | 8.2 |
| Mar 2026 | 7,038 | 2.53M | 0.28% | 6.8 ← PEAK |
| Apr 2026 | 5,794 | 2.00M | 0.29% | 7.9 |
| May 2026 | 5,054 | 1.88M | 0.27% | 9.8 |

⚠  Critical: Clicks dropped 28% (March → May). Average position fell from 6.8 → 9.8. 18 pages dropped from Top 10. This requires immediate diagnosis before any growth work begins.

Ahrefs Snapshot (June 2026)

| Metric | Value |
| --- | --- |
| Organic keywords | 1,552 |
| In positions 1–3 | 619 |
| Estimated monthly traffic | 16,126 |
| Monthly traffic value | $62,690 |
| Site health score | 99 / 100 |

MQL Funnel (HubSpot, Jan–May 2026)

| Metric | Value |
| --- | --- |
| Total MQL contacts (Organic + Direct) | 157 (~31/month) |
| Organic clicks / month (GSC avg) | ~6,600 |
| MQL conversion rate | ~0.47% of organic clicks |

Self-Reported Attribution (157 MQLs)

| Channel | Count | % |
| --- | --- | --- |
| Google | 49 | 31% |
| ChatGPT | 22 | 14% |
| AI tools (Gemini, Copilot, Claude, other) | 8 | 5.1% |
| Referral / Word-of-mouth | 5 | 3.2% |
| Blog / Content | 2 | 1.3% |
| Other / unclear | 71 | 45% |

Key insight: ~19% of MQLs explicitly cite AI search tools as their discovery channel — a growing segment with no current strategy.

2. Core Diagnosis: The Conversion Gap

The fundamental problem is a mismatch between traffic pages and MQL-converting pages.

Pages with the most organic traffic — but low commercial intent

| Page | Monthly Traffic | Top Keyword | Commercial Intent |
| --- | --- | --- | --- |
| /insider/restaurant-loyalty-programs | 1,692 | restaurant rewards programs | Low |
| / (homepage) | 1,714 | retail loyalty program software | High |
| /insider/sephora-beauty-insider | 514 | sephora tiers | Very Low |
| /insider/bank-loyalty-programs | 469 | bank loyalty programs | Low |
| /resources/10-best-mobile-loyalty-apps | 446 | loyalty app | Low |
| /insider/best-retail-loyalty-programs | 416 | loyalty program retail | Medium |
| /resources/10-best-gamification-programs | 392 | gamification rewards | Low |

Pages where MQLs actually come from — but low traffic

| Page | Est. MQL Count | Organic Traffic |
| --- | --- | --- |
| / (homepage) | ~60+ | 1,714 ✅ |
| /pricing | ~8 | Low ⚠ |
| /applications/white-label-loyalty | ~6 | 119 ⚠ |
| /technology/loyalty-program-api | ~4 | 90 ⚠ |
| /insider/best-loyalty-software-comparison-guide | ~4 | 107 ⚠ |

The opportunity: the pages that convert MQLs get very little organic traffic. The fastest path to 2× MQLs is routing more commercial-intent traffic to these high-converting pages — not just growing overall traffic.

3. Phase 0: Stop the Bleeding (June, Weeks 1–2)

Before building, fix what is breaking.

3.1  Diagnose the March → May Traffic Drop

18 pages dropped from Top 10; average position fell from 6.8 to 9.8 in two months.

☐  Pull the 18 pages that dropped from Top 10 in Ahrefs Site Audit

☐  Check correlation with a Google algorithm update (possible March 2026 core update)

☐  Compare page content freshness — were any key pages not updated recently?

☐  Check if competitors published competing content in February–March

☐  Review page speed / Core Web Vitals regressions in GSC

3.2  Fix the 1 Noindex Page Getting Organic Traffic

Site Audit flagged 1 noindex page receiving organic traffic — this leaks link equity.

☐  Identify the page in Site Audit

☐  Either remove the noindex tag (if the page should rank) or add a canonical / redirect

3.3  Submit 34 Pages to IndexNow

☐  Submit via IndexNow plugin or API — accelerates recrawling of updated content

3.4  Address Referring Domain Drop

3 referring domains were lost recently.

☐  Identify which domains dropped and why (expired content, redirected links?)

☐  Attempt to recover or replace with equivalent links

4. Q3: Convert More, Rank Higher on Commercial Keywords

Q3 Goal: 40 MQL/month by September (from 31 baseline).

Primary levers: improve conversion rate on existing traffic + quick-win keyword rankings.

Initiative 1: Commercial Keyword Quick Wins (July)

These keywords sit in positions 4–10. Pushing them into the top 3 can triple click-through rates (from ~5% to ~25%+).

| Keyword | Volume | KD | Current Pos | Page | Target |
| --- | --- | --- | --- | --- | --- |
| customer loyalty software | 700 | 49 | 5 | Homepage | Top 3 |
| loyalty platform | 600 | 62 | 4 | Homepage | Top 3 |
| loyalty management software | 350 | 54 | 4 | Homepage | Top 3 |
| limited time offer | 2,700 | 15 | 8 | /insider/time-limited-offer | Top 5 |
| loyalty card | 1,400 | 9 | 9 | /product/loyalty-card-system | Top 5 |
| loyalty management platform | 400 | 53 | 6 | Homepage | Top 3 |
| reward programs | 450 | 34 | 7 | /resources/top-40-rewards | Top 5 |

Homepage actions (highest priority — 1,714 traffic, $18k monthly value)

☐  Add explicit H2/H3 headers targeting 'customer loyalty software', 'loyalty platform', 'loyalty management software'

☐  Add a comparison table vs Antavo, LoyaltyLion, Smile.io with direct keyword mentions

☐  Improve meta title — test: 'Open Loyalty | #1 Customer Loyalty Software & Platform'

☐  Add Schema.org SoftwareApplication markup with explicit category tags

☐  Add internal links from top blog posts to homepage using exact-match anchor text

/insider/time-limited-offer (2,700 vol, KD 15, pos 8 — easiest high-volume win)

☐  Expand article depth: add examples, a framework/checklist section, data table

☐  Add internal CTAs linking to promotions module and gamification product pages

Initiative 2: Conversion Rate Optimisation on High-Traffic Pages (July–August)

The restaurant, Sephora, bank loyalty, and gamification articles get 1,700+ visits/month combined but send very few MQLs. Adding the right conversion elements changes this without new content.

For all major blog / insider posts

☐  Add a 'See how Open Loyalty powers [topic] programs → Book a Demo' CTA at 30% scroll mark (not just bottom)

☐  Add sticky sidebar or inline widget: 'Building a loyalty program? See our platform →'

☐  Create dedicated 'Loyalty Platform for [Restaurant/Retail/Finance]' landing pages and link from relevant posts

☐  Add exit-intent popup: 'Download our [industry] loyalty program benchmark report'

/insider/best-loyalty-software-comparison-guide (107 traffic, ~4 MQLs — highest converting page)

☐  Push from pos 3 → pos 1 for 'best customer loyalty program software'

☐  Expand with a 'vs' comparison section for Antavo, LoyaltyLion, Smile.io, Emarsys, Salesforce Loyalty

☐  Add trust signals: G2 / Capterra badges, customer logos, review quotes

☐  Target keyword cluster: 'loyalty software comparison', 'best loyalty software', 'loyalty platform comparison guide'

Initiative 3: Unlock Low-KD Keyword Gaps (August–September)

These keywords have high volume and very low difficulty but Open Loyalty ranks poorly — mainly because the pages are too thin or lack optimisation.

| Keyword | Volume | KD | Current Pos | Action |
| --- | --- | --- | --- | --- |
| gamification software | 1,600 | 5 | 37 | Expand existing article |
| customer retention mgmt software | 800 | 3 | 31 | Expand product page |
| customer retention software | 500 | 4 | 28 | Same product page |
| brand loyalty | 5,200 | 43 | 32 | Create cornerstone guide |
| how to build customer loyalty | 800 | 24 | 45 | Upgrade existing article |
| customer referral program | 600 | 37 | 50 | Build links to existing page |
| customer loyalty strategies | 450 | 12 | 49 | Upgrade existing article |

Brand loyalty article (5,200 vol, KD 43, pos 32) — single biggest gap

A top-5 ranking here alone adds ~650 clicks/month.

☐  Create a comprehensive 3,000+ word 'What is Brand Loyalty?' guide

☐  Structure: definition → why it matters → 5 stages → how to measure → tactics → how Open Loyalty helps

☐  Include data, examples (Nike, Apple, Amazon), and internal links to all product pages

Customer retention software (800 vol, KD 3–4, pos 28–31)

☐  Expand /product/customer-retention-software to 2,000+ words

☐  Add comparison table, case studies, and FAQ schema

☐  With KD of 3–4, this should reach top 5 within 4–6 weeks of publishing

Spanish language pages

MQLs already arriving from Spain, Colombia, Peru, Argentina, Honduras

Translate and localise top 5 commercial pages into Spanish

Target: 'software de fidelización', 'plataforma de lealtad', 'programa de fidelización empresarial'

5. Q4: Scale Volume and AI / GEO Strategy

Q4 Goal: 62 MQL/month by December (true 2× baseline).

Primary levers: content volume, link building, AI search optimisation, industry landing pages.

Initiative 4: Industry Landing Pages (October)

Your MQL contacts span many industries. Dedicated 'loyalty platform for [industry]' pages capture intent that blog posts cannot.

| Page URL | Primary Keyword | Volume | Rationale |
| --- | --- | --- | --- |
| /applications/loyalty-platform-for-retail | loyalty program for retail | 350 | Best-retail blog ranks #3 — no product CTA destination |
| /applications/loyalty-platform-for-finance | loyalty program for banks | 200 | Bank loyalty article gets 469 traffic/month |
| /applications/loyalty-platform-for-restaurants | restaurant loyalty software | 250 | Restaurant article gets 1,692 traffic/month |
| /applications/loyalty-platform-for-healthcare | loyalty for healthcare | 150 | 'gamification healthcare' keyword already converting MQLs |
| /applications/loyalty-platform-for-saas | saas loyalty program | 200 | /applications/saas-enrichment already ranks #1 |

Each page must include: value prop for that industry, client case study, industry-specific features, FAQ schema, demo CTA above the fold.

Initiative 5: AI / GEO Search Optimisation (October–November)

14% of MQLs cite ChatGPT; 19% cite AI tools overall. This will grow. Being cited by LLMs requires different optimisation than traditional Google SEO.

Entity optimisation

☐  Create or update an Open Loyalty Wikipedia / Wikidata entry (AI models cite structured knowledge graphs)

☐  Ensure consistent name, address, product description across Crunchbase, G2, Capterra, LinkedIn

☐  Create a factual /about/company page: founding year, HQ, product category, team size, deployment options

Structured data

☐  Add SoftwareApplication schema on all product pages (applicationCategory, operatingSystem, offers, aggregateRating)

☐  Add FAQPage schema on all blog posts — LLMs pull directly from FAQ structured data

☐  Add Organization schema on homepage with sameAs links to Crunchbase, G2, LinkedIn, Wikipedia

AI-friendly content

☐  Add a 'Quick Summary' box at the top of key pages with 3–5 bullet points — what LLMs excerpt when citing

☐  Publish a quarterly 'State of Loyalty' data report — LLMs and journalists cite original data heavily

G2 / Capterra review volume

☐  Actively solicit reviews from existing clients (minimum 25 reviews needed to appear in AI recommendation lists)

☐  Ensure category tags on G2/Capterra match target keywords: 'loyalty management software', 'customer loyalty software'

Initiative 6: Competitor Comparison Pages (November)

People searching 'Open Loyalty vs Antavo' are deep in the buying journey — highest-intent visitors you can get.

| Page | Competitor | Common Keywords | Their DR |
| --- | --- | --- | --- |
| /vs/antavo | Antavo | 260 | 73 |
| /vs/loyaltylion | LoyaltyLion | 236 | 76 |
| /vs/salesforce-loyalty | Salesforce Loyalty Mgmt | 90 | 92 |

☐  Create /vs/antavo — 'Open Loyalty vs Antavo: API-First vs Managed Service'

☐  Create /vs/loyaltylion — 'Open Loyalty vs LoyaltyLion: Enterprise vs SMB'

☐  Upgrade /best-loyalty-software to include 10 competitors with a structured comparison table

Initiative 7: Link Building (October–December, ongoing)

You are competing for KD 49–62 keywords against DR 73–78 sites (LoyaltyLion, Antavo, Smile.io). Closing the authority gap is essential for Q4 and beyond.

Tier 1: Digital PR (highest leverage)

☐  Publish the '2026 Loyalty Program Benchmarks' data report (use anonymised HubSpot + GSC data)

☐  Pitch to Loyalty360, RetailCustomerExperience, CustomerThink

☐  Target journalists covering loyalty marketing via LinkedIn + HARO

Tier 2: Guest posts

☐  Target: CustomerThink, Business2Community, Smile.io blog

☐  Topic angles: 'Why loyalty programs fail without API-first architecture', 'ROI of white-label loyalty in 2026'

Tier 3: Partnership links

☐  Request links from technology partners, integration partners, and enterprise clients

☐  Ensure all client case studies on your site are linked from the client's press / partner page

6. Technical SEO Cleanup (Parallel, Ongoing)

| Issue | Pages Affected | Priority | Action |
| --- | --- | --- | --- |
| Missing alt text | 383 | Medium | Bulk fix — describe image AND include keyword where natural |
| Meta description too long | 84 | Medium | Trim to 150–160 characters |
| Meta description too short | 47 | Medium | Expand to 120–160 characters |
| Title too long | 80 | Medium | Trim to 55–60 characters |
| SERP title ≠ page title | 79 | High | Google is rewriting your titles — align them |
| Title too short | 10 | Low | Expand with keyword + brand |
| Noindex page getting traffic | 1 | Critical | Remove noindex or add canonical |
| Noindex follow pages | 5 | Medium | Review if intentional |

7. Measurement Framework

Weekly (every Monday)

GSC clicks by landing page — focus on homepage, /pricing, /applications/, /technology/

Ranking changes for 20 priority keywords (see table below)

MQL count from previous week (HubSpot: source = organic/direct, lifecycle = MQL)

Monthly

Total organic MQL count vs 31/month baseline

Organic clicks vs 7,038/month March 2026 peak

Conversion rate: organic clicks → MQL (baseline: 0.47%)

AI attribution: % of MQLs citing ChatGPT/AI (baseline: 19%)

20 Priority Keywords to Track Weekly

| Keyword | Volume | Current Pos | Target |
| --- | --- | --- | --- |
| customer loyalty software | 700 | 5 | 1–2 |
| loyalty platform | 600 | 4 | 1–2 |
| loyalty management software | 350 | 4 | 1–3 |
| loyalty platform saas | 150 | 1 | Hold |
| loyalty program software | 500 | 3 | 1–2 |
| loyalty software | 600 | 1 | Hold |
| loyalty program api | 200 | 1 | Hold |
| brand loyalty | 5,200 | 32 | 5–10 |
| gamification software | 1,600 | 37 | 5–10 |
| customer retention software | 500 | 28 | 5–10 |
| customer retention management software | 800 | 31 | 5–10 |
| limited time offer | 2,700 | 8 | 4–6 |
| loyalty card | 1,400 | 9 | 4–6 |
| best loyalty software | 300 | 3 | 1–2 |
| white label loyalty | — | 2 | 1 |
| loyalty program management | 500 | 2 | 1 |
| referral program software | 800 | 20 | 5–10 |
| b2b loyalty platform | — | converting | Monitor |
| loyalty platform for retail | 350 | not ranking | 5–10 |
| plataforma de fidelización | — | 1 | Hold |

8. 12-Week Sprint Plan

| Period | Focus | Key Deliverables |
| --- | --- | --- |
| Weeks 1–2 Jun 16–30 | Triage | • Diagnose 18 pages that dropped from Top 10 • Fix noindex page • Submit 34 pages to IndexNow • Audit homepage meta title/description |
| Weeks 3–6 Jul 1–31 | Quick Wins | • Homepage H2/H3 + Schema.org markup • Expand /insider/time-limited-offer • Expand /product/customer-retention-software • Bulk fix: alt text (383 pages), meta descriptions, titles • Mid-funnel CTAs on top 10 traffic pages • Brief 'brand loyalty' cornerstone article |
| Weeks 7–10 Aug 4–31 | Content Push | • Publish 'brand loyalty' cornerstone (5,200 vol, KD 43) • Expand /insider/best-gamification-software • Upgrade /insider/best-loyalty-software-comparison-guide • Launch /applications/loyalty-platform-for-retail • Launch /applications/loyalty-platform-for-finance • Begin Spanish commercial page translations |
| Weeks 11–12 Sep 1–15 | CRO Review | • Review traffic / ranking changes from 8 weeks of work • A/B test homepage hero CTA text • Assess: are we at 40 MQL/month? Adjust Q4 priorities |
| Oct–Dec | Q4 Scale | • Industry pages: restaurants, healthcare, SaaS • AI/GEO: structured data, G2 reviews, Wikipedia entity • Competitor pages: /vs/antavo, /vs/loyaltylion • Link building outreach campaign • Publish 2026 Loyalty Benchmarks data report |

9. Expected Outcomes

| Metric | Baseline (May 2026) | Q3 Target (Sep) | Q4 Target (Dec) |
| --- | --- | --- | --- |
| Organic MQLs / month | 31 | 40 | 62 |
| Organic clicks / month | 5,054 | 7,500 | 10,000+ |
| Homepage commercial KW ranking | pos 3–5 avg | pos 1–3 avg | pos 1–2 avg |
| Keywords in top 3 | 619 | 750+ | 900+ |
| AI / GEO MQL attribution | 19% | 22% | 28% |

The 2× MQL target is achievable via three levers working together:

Recover lost rankings (the March→May drop = ~2,000 clicks/month lost — fixing this alone recovers significant ground)

Improve conversion rate on existing traffic (0.47% → 0.70% via better CTAs on high-traffic pages — adds ~15 MQLs/month with zero new content)

Grow commercial keyword rankings (homepage, product pages, comparison pages push the rest of the way)

Lever 2 alone — if the top 5 traffic pages each yield 1 additional MQL/month via better CTAs — adds 5 MQLs immediately with no new content required.